## Backlog
ID | Epic | User story | Acceptance criteria | Component | Priority | Points | Status | Spec ref
LZ-001 | Foundation & Developer Experience | As a developer, I want a one-command local stack so that I can run the whole system without manual setup | docker compose up brings up Postgres, LocalStack and the API; API health returns UP | Infra | Must | 5 | Done | Tech §5
LZ-002 | Foundation & Developer Experience | As a developer, I want the database schema created automatically so that environments never drift | Flyway applies V1 on startup; all 21 tables present; re-runs are no-ops | Backend | Must | 8 | Done | Tech §2
LZ-003 | Foundation & Developer Experience | As a developer, I want enum columns that map cleanly to JPA so that entities need no casting | Native enums replaced by varchar + CHECK; defaults and partial index preserved | Backend | Must | 3 | Done | Tech §2
LZ-004 | Foundation & Developer Experience | As a client developer, I want one error shape across every endpoint so that I parse errors in one place | All errors return code/message/fields/timestamp; codes are stable and documented | Backend | Must | 3 | Done | —
LZ-005 | Foundation & Developer Experience | As a client developer, I want a generated API client so that backend and app cannot drift | OpenAPI served at /v3/api-docs; Dart client generated from it; regeneration documented | Shared | Must | 5 | Done | —
LZ-006 | Foundation & Developer Experience | As a developer, I want CI on every push so that regressions are caught before merge | Backend and Flutter tests run on push; failures block the merge | Infra | Must | 3 | Not Started | —
LZ-007 | Foundation & Developer Experience | As a developer, I want seed data so that screens can be built against realistic records | One landlord, one property with a bedspace and a whole unit, leases and billing periods | Backend | Should | 3 | Not Started | —
LZ-008 | Foundation & Developer Experience | As a developer, I want integration tests against real Postgres so that schema constraints are exercised | Testcontainers suite runs in CI; partial indexes and CHECKs are covered | Backend | Must | 5 | In Progress | —
LZ-009 | Foundation & Developer Experience | As a developer, I want money and date conventions fixed so that rounding never drifts | BigDecimal for peso amounts, LocalDate for due dates, UTC for instants; documented | Backend | Should | 2 | Not Started | Tech §7
LZ-010 | Design System | As a designer, I want the design language as code so that both apps look like one product | Colour and type tokens match design language v2; shared package consumed by both apps | Shared | Must | 5 | Done | Design v2
LZ-011 | Design System | As a landlord, I want status shown consistently so that I can scan a long list quickly | Dot+pill chip; teal=paid, amber=pending, red=overdue; mapping covered by tests | Shared | Must | 2 | Done | Design v2
LZ-012 | Design System | As a user, I want the app to feel distinctly Filipino so that it does not read as generic software | Capiz-lattice header renders at low contrast behind content on both apps | Shared | Should | 3 | Done | Design v2
LZ-013 | Design System | As a user, I want the app to render correctly offline so that type does not shift on first launch | Space Grotesk, Manrope and IBM Plex Mono bundled as assets; goldens verify type | Shared | Should | 3 | Not Started | Design v2
LZ-020 | Accounts & Access | As a new user, I want to create an account with email or phone so that I can use Lizmo without an email address | Either identifier accepted; duplicate gives a specific code; tenant profile always created | Backend | Must | 5 | Done | Product §2.5
LZ-021 | Accounts & Access | As a returning user, I want to sign in so that I can reach my own data | Email or phone plus password; wrong credentials and unknown account give the same error | Backend | Must | 3 | Done | Product §2.5
LZ-022 | Accounts & Access | As a user, I want to stay signed in between launches so that I do not re-enter my password daily | Refresh token stored securely; rotates on use; replay is rejected | Mobile | Must | 5 | Done | Tech §4
LZ-023 | Accounts & Access | As a user, I want a sign-in screen that tells me what went wrong so that I can correct it | Field validation before submit; server errors shown inline; password can be revealed | Mobile | Must | 3 | Done | Design v2
LZ-024 | Accounts & Access | As a user, I want to sign out so that my session cannot be reused on a shared device | Refresh token revoked server-side; local tokens cleared; idempotent | Mobile | Must | 2 | Done | Tech §4
LZ-025 | Accounts & Access | As a user holding several roles, I want to switch context so that I can act as tenant or landlord | Switcher appears only when more than one profile exists; switching changes navigation | Mobile | Must | 8 | Not Started | Product §2.5
LZ-026 | Accounts & Access | As a landlord, I want my data invisible to other landlords so that my business stays private | Ownership checks on every property-scoped resource; cross-tenant access returns 403 | Backend | Must | 8 | Not Started | Tech §4
LZ-027 | Accounts & Access | As a tenant, I want only my own records visible so that other tenants cannot see my payments | Tenant self-scope enforced on lease, payment, maintenance and notification reads | Backend | Must | 5 | Not Started | Tech §4
LZ-028 | Accounts & Access | As a user, I want to reset a forgotten password so that I am not locked out permanently | Reset requested by email or phone; single-use time-limited token; old sessions revoked | Backend | Should | 5 | Not Started | —
LZ-029 | Accounts & Access | As a user, I want to edit my name and contact details so that my account stays current | Name, email and phone editable; uniqueness enforced; contact rule still satisfied | Mobile | Should | 3 | Not Started | —
LZ-030 | Property, Unit & Bed | As a landlord, I want to add a property so that I can manage its units in Lizmo | Name, address and type captured; property appears in my list only | Backend | Must | 3 | Not Started | Product §2.1
LZ-031 | Property, Unit & Bed | As a landlord, I want to add units to a property so that each can be rented separately | Unit number unique per property; rental mode set at creation; rent independent per unit | Backend | Must | 5 | Not Started | Product §2.1
LZ-032 | Property, Unit & Bed | As a landlord, I want to define beds in a shared room so that I can rent bedspaces individually | Beds only on BEDSPACE units; label unique per unit; each has its own status | Backend | Must | 5 | Not Started | Product §2.1
LZ-033 | Property, Unit & Bed | As a landlord, I want to mark a bed under maintenance so that it is not counted as rentable | Bed status independent of tenancy; excluded from occupancy and platform billing | Backend | Should | 3 | Not Started | Product §2.1
LZ-034 | Property, Unit & Bed | As a landlord, I want to see occupancy at a glance so that I know what is empty | Occupancy derived from active leases, never stored; shown per property and per unit | Mobile | Must | 5 | Not Started | Product §2.9
LZ-035 | Property, Unit & Bed | As a landlord, I want my property list on my phone so that I can check it away from a desk | List renders with design system; empty state guides first property creation | Mobile | Must | 5 | Not Started | Design v2
LZ-040 | Leases | As a landlord, I want to create a lease so that a tenant is formally attached to a unit or bed | Bed required for BEDSPACE, forbidden otherwise; one active lease per bed enforced | Backend | Must | 8 | Not Started | Product §2.2
LZ-041 | Leases | As a landlord, I want to set the due day myself so that all my tenants pay on the same date | Due day 1-31, set per lease and independent of move-in date | Backend | Must | 2 | Not Started | Product §2.2
LZ-042 | Leases | As a landlord, I want to end a lease so that the bed becomes available again | Status moves to ENDED or TERMINATED; bed frees up; billing history is retained | Backend | Must | 3 | Not Started | Product §2.2
LZ-043 | Leases | As a returning tenant, I want my history preserved so that re-renting does not duplicate me | New lease attaches to the existing tenant profile; prior leases remain visible | Backend | Should | 3 | Not Started | Product §2.2
LZ-044 | Leases | As a tenant, I want to see my lease details so that I know what I owe and when | Rent, due day, unit or bed, start and end dates shown; amounts in mono type | Mobile | Must | 5 | Not Started | Design v2
LZ-050 | Billing & Payments | As a landlord, I want billing periods generated automatically so that overdue rent is tracked without me | One period per lease per cycle, created regardless of payment; unique per lease and start | Backend | Must | 8 | Not Started | Product §2.3
LZ-051 | Billing & Payments | As a tenant, I want to submit proof of payment so that I can pay by GCash without a gateway | Amount, date, method and proof image captured; status starts PENDING_VERIFICATION | Backend | Must | 8 | Not Started | Product §2.3
LZ-052 | Billing & Payments | As a tenant, I want the oldest unpaid period pre-selected so that I do not misapply a payment | Dropdown lists unpaid and partial only, oldest first, oldest pre-selected, override allowed | Mobile | Must | 5 | Not Started | Product §2.3
LZ-053 | Billing & Payments | As a landlord, I want to confirm a payment so that the tenant's balance updates | Confirm applies amount to the period and recomputes status; verifier and time recorded | Backend | Must | 5 | Not Started | Product §2.3
LZ-054 | Billing & Payments | As a landlord, I want to reject a payment with a reason so that the tenant knows what to fix | Rejection requires remarks; tenant notified; resubmission allowed | Backend | Must | 3 | Not Started | Product §2.3
LZ-055 | Billing & Payments | As a tenant, I want to pay in instalments so that a partial payment still counts | Multiple payments apply to one period; status becomes PARTIALLY_PAID until covered | Backend | Should | 5 | Not Started | Product §2.3
LZ-056 | Billing & Payments | As a tenant, I want to upload a photo from my phone so that submitting proof is quick | Camera or gallery; image uploaded via presigned URL; retry on failure | Mobile | Must | 5 | Not Started | Tech §7
LZ-057 | Billing & Payments | As a landlord, I want a queue of payments awaiting review so that nothing is missed | Pending payments listed oldest first with proof preview and confirm/reject actions | Mobile | Must | 5 | Not Started | Design v2
LZ-058 | Billing & Payments | As a landlord, I want the rent roll for a month so that I can see who has paid | All periods for the month with tenant, amount and status; matches the v2 mockup | Mobile | Must | 5 | Not Started | Design v2
LZ-060 | Maintenance | As a tenant, I want to report a problem in plain words so that I do not have to categorise it | Free-text description with optional photo; no categories or priorities | Backend | Must | 5 | Not Started | Product §2.4
LZ-061 | Maintenance | As a landlord, I want to update a request's status so that the tenant knows it is being handled | Status transitions with optional remarks; resolved timestamp recorded | Backend | Must | 3 | Not Started | Product §2.4
LZ-062 | Maintenance | As a tenant, I want to follow my request so that I am not left wondering | Own requests listed with current status; updates appear without reinstalling | Mobile | Must | 3 | Not Started | Product §2.4
LZ-070 | Staff | As a landlord, I want to assign a caretaker to one property so that they can help without seeing everything | Assignment scoped to a single property; same person assignable to several with separate permissions | Backend | Must | 5 | Not Started | Product §2.5
LZ-071 | Staff | As a landlord, I want to choose what my staff can do so that trust is granular | Permissions selected per assignment from the MVP set; lease management excluded | Backend | Must | 5 | Not Started | Product §2.5
LZ-072 | Staff | As a landlord, I want to revoke access immediately so that a departing caretaker loses it at once | Deactivation takes effect on the next request; no waiting for token expiry | Backend | Must | 5 | Not Started | Tech §4
LZ-073 | Staff | As a caretaker, I want to see the properties I help with so that I can switch between landlords | Own assignments listed across landlords with the permissions held on each | Mobile | Should | 3 | Not Started | Product §2.5
LZ-080 | Documents | As a landlord, I want to attach a signed contract to a lease so that the paperwork lives with the record | Upload against property, unit, lease or tenant; type and label captured | Backend | Should | 5 | Not Started | Product §2.6
LZ-081 | Documents | As a user, I want uploads to go straight to storage so that large files do not stall the app | Presigned URL issued by the API; binary never proxied through the backend | Backend | Should | 5 | Not Started | Tech §7
LZ-082 | Documents | As a landlord, I want to remove a document so that mistakes can be corrected | Delete removes the record and the stored object; permitted only to the owner | Backend | Could | 2 | Not Started | Product §2.6
LZ-090 | Notices | As a landlord, I want to post a notice to all my tenants so that I can announce things once | Scope selectable; ALL_TENANTS evaluated dynamically so later tenants still see it | Backend | Should | 5 | Not Started | Product §2.7
LZ-091 | Notices | As a landlord, I want to know who has read a notice so that I can follow up individually | Read receipts per tenant; unread tenants identifiable | Backend | Should | 3 | Not Started | Product §2.7
LZ-092 | Notices | As a landlord, I want notices to expire so that old announcements disappear on their own | Expiry date optional; expired and archived notices leave the active feed | Backend | Should | 3 | Not Started | Product §2.7
LZ-093 | Notices | As a tenant, I want a feed of current notices so that I see what affects me | Active notices only, scoped to me, marked read on view | Mobile | Should | 3 | Not Started | Product §2.7
LZ-100 | Notifications | As a tenant, I want a reminder before rent is due so that I do not miss it | Notification raised ahead of due date and again once overdue | Backend | Should | 5 | Not Started | Product §2.8
LZ-101 | Notifications | As a tenant, I want to know when my payment is confirmed so that I have certainty | Confirmation and rejection both notify, rejection carrying the landlord's remarks | Backend | Should | 3 | Not Started | Product §2.8
LZ-102 | Notifications | As a user, I want to see my notifications in one place so that nothing is buried | List with unread state; marking read persists across devices | Mobile | Should | 3 | Not Started | Product §2.8
LZ-110 | Reporting | As a landlord, I want an occupancy report so that I can see how much inventory sits empty | Units and beds occupied versus vacant, per property, computed live | Backend | Should | 3 | Not Started | Product §2.9
LZ-111 | Reporting | As a landlord, I want an income summary so that I know what actually came in | Confirmed payments only, by property and month | Backend | Should | 3 | Not Started | Product §2.9
LZ-112 | Reporting | As a landlord, I want a list of overdue tenants so that I know who to chase | Leases with unpaid or overdue periods, oldest first | Backend | Should | 3 | Not Started | Product §2.9
LZ-113 | Reporting | As a landlord, I want a dashboard on opening the app so that I see the state of things immediately | Occupancy and overdue totals in the header; matches the v2 mockup | Mobile | Should | 5 | Not Started | Design v2
LZ-120 | Platform Billing | As Lizmo, I want to invoice each landlord monthly so that revenue is collected per occupied slot | Snapshot on the billing date; units x150 + bedspaces x50; one cycle per landlord per date | Backend | Must | 8 | Not Started | Product §3
LZ-121 | Platform Billing | As a landlord, I want to pay Lizmo the same way my tenants pay me so that the process is familiar | Proof-of-payment upload against a billing cycle; awaits admin confirmation | Backend | Must | 5 | Not Started | Product §3
LZ-122 | Platform Billing | As Lizmo, I want unpaid accounts locked after the grace period so that the model is enforceable | Overdue at due date, warning sent, LOCKED after 7 days; tenants remain unaffected | Backend | Must | 8 | Not Started | Product §3
LZ-123 | Platform Billing | As a locked-out landlord, I want to be told exactly why so that I can fix it immediately | Management writes return ACCOUNT_LOCKED_UNPAID_INVOICE; app routes to the unpaid invoice | Backend | Must | 5 | Not Started | Tech §4
LZ-124 | Platform Billing | As a landlord, I want lockout lifted as soon as I pay so that I am not waiting on a person | Confirming the last overdue cycle restores ACTIVE in the same transaction | Backend | Must | 3 | Not Started | Product §3
LZ-125 | Platform Billing | As a landlord, I want to see my Lizmo invoices so that I can check what I am charged for | Cycle list with slot counts and amounts; unpaid ones surfaced first | Mobile | Should | 5 | Not Started | Product §3
LZ-130 | Admin Console | As a Lizmo admin, I want a queue of platform payments so that I can verify them in order | Pending payments listed with landlord, amount, method and proof; oldest first | Admin Web | Must | 5 | In Progress | Tech §3.9
LZ-131 | Admin Console | As a Lizmo admin, I want to confirm or reject a payment so that accounts reflect reality | Confirm and reject available only on pending rows; rejection requires remarks | Admin Web | Must | 5 | Not Started | Tech §3.9
LZ-132 | Admin Console | As a Lizmo admin, I want admin routes closed to everyone else so that landlords cannot self-approve | Routes require a platform_admins record; landlord staff are refused | Backend | Must | 5 | Not Started | Tech §3.9
LZ-133 | Admin Console | As a Lizmo admin, I want to see overdue accounts so that I can chase them before lockout | Filterable by status; locked accounts distinguishable at a glance | Admin Web | Should | 3 | Not Started | Tech §3.9
LZ-140 | Deployment & Operations | As an operator, I want infrastructure defined as code so that the environment is reproducible | Terraform for Cloud Run, Storage, Secret Manager, Artifact Registry and Scheduler | Infra | Must | 8 | In Progress | infra/gcp
LZ-141 | Deployment & Operations | As an operator, I want a budget alert so that a free-tier project cannot bill me silently | Alert configured with a threshold; notification reaches a real address | Infra | Must | 2 | Not Started | infra/gcp
LZ-142 | Deployment & Operations | As a developer, I want pushes deployed automatically so that releasing is not a manual ritual | Image built, pushed and deployed to Cloud Run on merge to main | Infra | Should | 5 | Not Started | infra/gcp
LZ-143 | Deployment & Operations | As an operator, I want scheduled jobs to run outside the app so that they fire while it sleeps | Cloud Scheduler invokes internal endpoints with OIDC; endpoints verify the token | Backend | Must | 5 | Not Started | infra/gcp
LZ-144 | Deployment & Operations | As an operator, I want production storage on Cloud Storage so that the last AWS dependency is gone | S3 client replaced; presigned URLs issued via the service account | Backend | Must | 5 | Not Started | infra/gcp
LZ-145 | Deployment & Operations | As an operator, I want alerting on the API so that I hear about downtime before users do | Uptime check on /actuator/health with a notification channel | Infra | Should | 3 | Not Started | —

## Epics
Epic ID | Epic | Goal | Stories | Points | Done | Points done | % complete
E1 | Foundation & Developer Experience | The stack runs locally, the schema is versioned, and contracts are generated rather than hand-kept
E2 | Design System | One visual language, shared by both clients, matching design language v2
E3 | Accounts & Access | Identity, sessions, and the authorisation rules that keep landlords and tenants apart
E4 | Property, Unit & Bed | The rentable inventory, including bedspaces as first-class things
E5 | Leases | Attaching a tenant to a unit or bed, with landlord-controlled due dates
E6 | Billing & Payments | Rent tracked per period and settled by proof-of-payment, with no gateway
E7 | Maintenance | Tenants report problems in plain words; landlords track them to done
E8 | Staff | Per-property caretakers with granular, revocable permissions
E9 | Documents | Contracts, IDs and receipts attached to the record they belong to
E10 | Notices | Announcements with dynamic audience, expiry and read receipts
E11 | Notifications | In-app signals for rent, payments, maintenance and notices
E12 | Reporting | Occupancy, income, overdue and maintenance views over live data
E13 | Platform Billing | Lizmo's own revenue: per-slot invoicing, collection and enforcement
E14 | Admin Console | Internal tooling for verifying platform payments and chasing overdue accounts
E15 | Deployment & Operations | Reproducible infrastructure, automated releases and basic observability
Total

## Legend
Field | Value | Meaning
Status | Done | Built and verified against a running system
Status | In Progress | Started; see the note in the commit history for what remains
Status | Not Started | Not begun
Status | Blocked | Cannot proceed until something else lands
Priority | Must | MVP does not ship without it
Priority | Should | Expected in MVP, but could slip a release
Priority | Could | Valuable, not expected in MVP
Points | 1, 2, 3, 5, 8 | Relative effort, Fibonacci. 8 signals a story worth splitting
Component | Backend | Spring Boot API
Component | Mobile | Flutter app for landlord, tenant and staff
Component | Admin Web | Flutter web console for Lizmo staff
Component | Shared | Design system or generated client, used by both apps
Component | Infra | Docker, Terraform, CI
Spec ref | Product §n | Section of Lizmo_Product_Spec_v1.md
Spec ref | Tech §n | Section of Lizmo_Tech_Spec_v1.md
Spec ref | Design v2 | lizmo_design_language_v2.html, the canonical design language
Note | Statuses reflect the repository as of 14 Aug 2026. Stories are derived from Lizmo_Product_Spec_v1.md and Lizmo_Tech_Spec_v1.md; estimates are first-pass and unvalidated by any completed sprint.